Terms of Reference (TOR) for

Consultancy Service for Dam Safety Assessment, Development of Dam Safety Management Program, and Rehabilitation Oversight Services for Ethiopian Electric Power (EEP)

July, 2025.

Table of Contents.

1.	Introduction	3

2.	Background	3

3.	Objectives	4

4.	Scope of Work	5

5.	Deliverables	12

6.	Timeline/ Schedule	12

7.	Reporting	13

8.	Consultant’s team and Qualifications	14

9.	Consultant’s proposal	16

10.	Client’s support	17

11.	List of enclosure	17

- Introduction

The objective of this consultancy is to engage a qualified engineering consulting firm to assess the condition and safety of selected hydropower dams and appurtenant structures operated by Ethiopian Electric Power (EEP) and to develop and implement a Dam Safety Management System (DSMS) aligned with international best practices. The Consultant will also provide capacity building and training to EEP personnel to institutionalize dam safety practices and knowledge.

- Background

Ethiopia has made substantial investments in hydropower development, leading to a rapid expansion of hydropower capacity. By 2024, Ethiopia's installed hydropower capacity reached 4.7 GW, with ambitious plans to elevate it to 15 GW by 2030. Hydropower development in Ethiopia presents a complex interplay of benefits and challenges, necessitating a thorough assessment of its implications for continuous improvement and the long-term sustainability of the schemes.

Hydropower offers a promising pathway for Ethiopia’s sustainable energy future. As a renewable and carbon-free energy source, it aligns with the country’s commitment to environmental stewardship. In addition to environmental benefits, hydropower development contributes to economic growth and helps alleviate energy poverty, particularly in rural areas. Recognizing these advantages, the Ethiopian government has launched numerous hydropower initiatives.

Ethiopian Electric Power (EEP) is responsible for managing a significant portfolio of dams and hydropower projects across the country. Many of these projects include large reservoirs for water storage, which are critical for reliable energy generation and resource management.

EEP is seeking to undertake a comprehensive assessment of the condition of its dams and hydropower facilities to identify potential risks and hazards, prioritize maintenance and repair strategies, and develop a dam safety management program that aligns with best practices and international standards.

Ethiopian Electric Power (EEP) responsible for the management of a large portfolio of dams and hydropower projects in Ethiopia. Many of these projects include large, retained water storage reservoirs. The list of EEP generation assets with large, dammed reservoirs includes:

Table 1: List of Generation Assets

| No, | Project Name |
| --- | --- |
| 1 | Gibe III HEPP Dam |
| 2 | Tana Beles (Lake) |
| 3 | Tekeze |
| 4 | Melka Wakena |
| 5 | Koka |
| 6 | Gibe 1 |
| 7 | Genale Dawa III |
| 8 | Fincha main dam plus Amerti reservoir |
| 9 | Fincha Amerti Neshe |
| 10 | Grand Ethiopian Renaissance Dam (GERD) |
| 11 | Gibe II |
| 12 | Tis Abay I/II |
| 13 | Awash II,&III |

N.B. basic features of all the hydropower plant dams are enclose under Annex-1. EEP is now seeking the service of a consultant to undertake a comprehensive assessment of the condition of its dams and hydropower facilities in the context of dam safety management. In order to identify potential risks and hazards, prioritize maintenance and repair strategies, and develop a dam safety management program that aligns with best practices and industry standards.

- Objectives

The consultancy service has seven main objectives.

- Objective 1: Review existing national policies, dam safety management practices within EEP, and available documentation for 13 hydropower projects.

- Objective 2: Assess the current safety conditions of 13 hydropower projects.

- Objective 3: Conduct a comprehensive dam safety assessment of nine large storage dams, including the Gibe III Dam.

- Objective 4: Provide design, cost estimates, and monitoring rehabilitation works as the Employer’s Representative, aligned with PFMA results.

- Objective 5: Conduct audits and performance reviews to ensure continuous improvement, regulatory compliance, and effective implementation of dam safety programs.

- Objective 6: Develop and implement a comprehensive Dam Safety Management Program (DSMP), including operations and maintenance (O&M), monitoring, inspections, and capacity building.

- Objective 7: Identify overall capacity-building needs to strengthen EEP’s institutional capacity in dam safety by delivering targeted training, practical assistance, and knowledge transfer, with the goal of establishing a self-sustaining dam safety culture.

### Scope of Work

- The Consultant is expected to further develop a detailed Scope of Work to effectively achieve the objectives outlined above. A task-based approach, to be implemented in phases, is recommended for the successful delivery of these objectives. Additional tasks may be identified during the course of the assignment and, if necessary, will be assigned by EEP under separate agreements. The main tasks under this consultancy service include, but are not limited to, the following:

  - Task 1 Conduct Office-Based Review of existing national policies, dam safety management practice in EEP and 13 Projects’ available Documentations. (input time 60 days)

Shortly after the commencement of the services, the Consultant shall conduct an inception mission at EEP’s offices in order to better organize the Consultants’ activities and missions that require the Client’s involvement and collection of input data.

Specific Tasks:

- Review existing national policies related to dam safety to identify applicable compliance requirements.

- Review Ethiopian Electric Power’s (EEP) existing dam safety programs (existing dam safety management practice) to identify gaps and assess alignment with international standards.

- Review available documentation provided by the client—including design, construction, operation and maintenance (O&M), instrumentation, inspection, emergency planning, and rehabilitation records—for thirteen EEP hydropower projects, to assess site conditions, operational history, and the performance of the dams and associated hydroelectric facilities. Based on the review of the documentation, area to be focused during site inspection will be identified before going to the site.

Deliverables of Task 1:

- National and Institutional Dam Safety Practice Review Report identifying gaps

- Desktop Review Report on the Design, Operation, Monitoring, Maintenance, and Performance of 13 EEP Hydropower Projects identifying priority areas for the field assessment

- Audit Questionnaires.

  - Task 2: Current Safety Condition Assessment of 13 Hydropower Projects (input time 90 days)

The Consultant shall conduct comprehensive condition and risk assessments for 13 hydropower projects managed by Ethiopian Electric Power (EEP), with the objective of identifying structural, operational, and safety-related deficiencies that require mitigation.

The Specific Tasks under Task 2 shall include, but not be limited to, the following activities:

- Conduct a comprehensive condition assessment of all 13 hydropower projects, covering both dam structures and associated power generation facilities, with a focus on identifying structural, mechanical, and operational deficiencies.

- Perform detailed on-site inspections of key components, including:

- Water-retaining structures: dam body, abutments, spillways, outlet works, gates

- Power infrastructure: powerhouses, turbines, valves, cranes, drainage tunnels, and switchyards

- Reservoir area, abutments and reservoir rim slopes

- Evaluate original design parameters, construction methods, and subsequent modifications, and compare them with current operational practices and observed performance.

- Analyze instrumentation data for both concrete and embankment dams, comparing actual measurements against design expectations to assess structural behavior and performance trends.

- Assess the condition, functionality, reliability, and coverage of existing dam safety instrumentation, and identify any obsolete, malfunctioning, or missing equipment.

- Conduct advanced statistical analyses, including pendulum displacement trends and other time-series evaluations, to identify long-term deformation, instability, or other safety concerns.

- Assess the adequacy, coverage, and functionality of existing dam safety monitoring systems, identify equipment gaps or obsolete technologies, and provide site-specific recommendations for upgrades or new installations.

- Review completed audit questionnaires and integrate findings into the overall safety and performance evaluation.

- Provide overall technical recommendations detail study or improvement measures needed.

Deliverables of Task 2:

A comprehensive report summarizing the findings of the condition assessments for 13 hydropower projects, including:

- Detailed documentation of identified structural, operational, and safety deficiencies

- Project-specific recommendations for immediate, short-term, and long-term remedial measures, prioritized based on risk and severity

- Preliminary identification of potential intervention measures, with technical justifications and readiness levels

- Clear guidance on the scope and focus of next-phase detailed assessments or investigations required to address critical gaps or uncertainties including Potential Dam Failure Mode Analysis

  - Task 3: Conduct a comprehensive dam safety assessment of Nine large (120 input days)

The Consultant shall conduct a detailed dam safety assessment of nine large storage dams, including the Gibe III Dam, based on the recommendations provided under Task 2.

The specific tasks under this assignment shall include, but are not limited to, the following:

  - Perform a detailed dam safety evaluation of the Gibe III Dam and eight other large storage dams, including a comprehensive dam Potential Failure Mode Analysis (PFMA) update for all nine dams in accordance with the recommendation provided under objective 2.

  - Identify the most critical Potential Failure Modes (PFMs) that have a high or very high likelihood of occurrence and could lead to significant or extensive damage, including potential loss of life. This should be done using an initial risk matrix, and should include the corresponding risk category, prioritization, and recommended actions to mitigate identified risks.

  - Identify Applicable Instrumentation Modernization Plan: Provide recommendations for the replacement, upgrade, or installation of dam safety instrumentation to ensure full functionality, reliability, and coverage, including remote data acquisition, centralized data management, and integration with real-time risk assessment and decision-support tools.

  - Conceptual Design and Preliminary Cost Estimate of Rehabilitation Works Align with PFMA results.

  - Updates EAP in alignment with PFMA findings.

  - Recommend additional investigations, where necessary, to address data gaps or uncertainties related to dam safety.

  - Identify required rehabilitation works for each dam to address observed or potential safety deficiencies.

  - Determine project-specific capacity building needs and recommend the development or enhancement of a Dam Safety Management System (DSMS) tailored to each dam's context.

Deliverables of Task 3:

A comprehensive report for 9 dams selected dams that include:

- Potential Failure Mode Analysis (PFMA) for each dam, identifying credible failure modes and assessing their likelihood and potential consequences.

- Recommendations for additional investigations where information gaps or uncertainties are identified.

- Preliminary designs and cost estimates for priority safety intervention measures to address identified risks.

- A prioritized action plan to guide the next phase of detailed design and implementation.

- Updated EAP in alignment with PFMA findings.

### Task 4: Oversight and Monitoring of Rehabilitation Works as Employer Representative (100 in put days)

Based on specific requests from the Clients the consultant will follow up the implementation of the remedial works.  The specific tasks under this assignment shall include, but are not limited to, the following:

  - Provide engineering support and oversight for the planning, design, and implementation of remedial works identified through the Gibe III Dam and others under specific objective 4, ensuring alignment with PFA and dam safety priorities.

  - Review and validate rehabilitation designs to ensure technical adequacy, safety compliance, and adherence to applicable standards.

  - Oversee the execution of rehabilitation activities for the Gibe III Hydroelectric Project and others as needed, ensuring timely delivery, structural integrity, and reliable operation.

### Deliverable of Task 4

- Intervention Measures Design Review Report

- Final Oversight Summary Report

### Task 5: Develop and implement a comprehensive Dam Safety Management Program (DSMP), including O&M, monitoring, inspections and Capacity building (75 input days).

The Consultant shall develop, implement, and oversee the application of a comprehensive Dam Safety Management Program (DSMP) for Ethiopian Electric Power (EEP), drawing on the results of the condition assessments, instrumentation evaluations, and the Gibe III investigation conducted under Task A. The DSMP shall provide a formal framework for dam safety planning, risk assessment, inspection, monitoring, and emergency preparedness across EEP’s hydropower portfolio. The task includes capacity building, technical integration, and periodic audits to ensure sustainable and standardized dam safety practices aligned with Ethiopian regulatory requirements and international best practices (e.g., ICOLD, World Bank ESF).

    - Program Development

- Design a comprehensive DSMP customized to EEP’s institutional structure, operational procedures, and dam portfolio.

- Integrate technical findings (e.g., PFMA, instrumentation gaps, structural deficiencies) from previous assessments.

- Establish core program components: inspection protocols, risk classification, data management, reporting, governance structure, and escalation procedures.

- Align the DSMP with Ethiopian dam safety regulations and international best practices.

    - Program Implementation

- Provide technical support to roll out the DSMP at EEP headquarters and across all 13 project sites.

- Assist in integrating the DSMP into EEP’s existing operational systems and management workflows.

- Establish roles and responsibilities across organizational levels to ensure consistent program application.

- Support adoption of standard operating procedures, inspection forms, risk registers, and monitoring routines.

    - Program Auditing

- Conduct two formal audits (every two years) of DSMP implementation and compliance at both organizational and site levels.

- Assess:

  - Adherence to inspection schedules, SOPs, and reporting standards

  - Effectiveness of monitoring systems and risk controls

  - Roles, responsibilities, and institutional coordination

- Identify gaps and provide actionable recommendations to improve dam safety performance and accountability.

    - Emergency Preparedness Review

- Review and update Emergency Action Plans (EAPs) for all 13 sites.

- Provide clear, site-specific recommendations to ensure EAPs  reflect current conditions and risks.

Task 5: Deliverables

- Dam Safety Management Program Document: A complete DSMP framework customized to EEP's needs and aligned with international standards.

- Dam Safety Management Program Implementation Toolkit: SOPs, inspection forms, risk matrices, and management tools for use by EEP staff.

- Audit Reports: Formal audit documentation highlighting implementation status, findings, and improvement recommendations.

- Updated EAP for all the project sites

  - Task 6: Audits and performance reviews to ensure improvement, regulatory compliance, and effective implementation of dam safety programs (60 days).

### Conduct periodic audits and performance reviews of 13 hydropower projects operated by Ethiopian Electric Power (EEP) over four years to ensure ongoing compliance with national and international dam safety standards. This includes follow-up inspections to assess facility conditions, verify the implementation of corrective actions, and strengthen EEP’s internal capacity for effective dam safety management and continuous improvement.

### Specific Tasks:

  - Develop a standardized audit framework to evaluate the effectiveness of dam safety management systems, operational procedures, and emergency preparedness measures.

  - Conduct regular internal audits during project periods (every 2 years) of dam safety practices, including inspections, documentation, monitoring systems, and maintenance activities.

  - To support capacity building within EEP by facilitating direct knowledge transfer during inspections, mentoring designated EEP staff on dam safety inspection techniques, reporting, and alignment with EEP’s dam safety policies

  - Evaluate the performance of rehabilitation measures, monitoring instrumentation, and O&M systems to ensure they meet design intent and safety objectives.

  - Assess compliance with national regulations, international best practices, and internal DSMP protocols, identifying any gaps or non-conformities.

  - Provide actionable recommendations for corrective measures and system improvements based on audit findings and performance reviews.

  - Track implementation of previous audit recommendations and maintain a performance dashboard to monitor progress, ensure accountability, and support decision-making.

Deliverables of Task 6:

The following deliverables shall be prepared for each project that is inspected. The deliverables can be grouped in a single report gathering all required information:

- Regular Inspection and Audit Report – The report will summarize the mission, describe the inspections, present observations with photograph documentation, review of available instrumentation data (as necessary), updated list of deficiencies, describe modifications or improvements, assess performance, provide recommendations for further engineering analysis or remedials actions. Both Draft and Final reports shall be issued.

- Knowledge transfer – Identify EEP staff to attend site visits with inspectors. Inspectors to knowledge transfer and where appropriate provide training of EEP staff in dam safety inspection, deficiency identification, and reporting to EEP dam safety policies.

- Video Conference – Within 15 days of issuing the Draft report, the Engineering Consultant shall present its report by video conference or in the EEP Addis Ababa main office.

  - Task 7: Capacity Building (75 total in put days).

Overall capacity-building to strengthen EEP’s institutional capacity in dam safety by delivering targeted training, practical assistance, and knowledge transfer, with the goal of establishing a self-sustaining dam safety culture is very important during this service. Thus, the Consultant shall design and deliver a comprehensive dam safety training program for Ethiopian Electric Power (EEP), targeting managers, dam safety staff, plant operators, instrumentation personnel, emergency response teams, and other key professionals. Training sessions will be conducted in coordination with EEP at its headquarters in Addis Ababa.

The program will include:

- Local training for 40-day in total for safety professionals, delivered in different time for 20 participants per round.

- International study tours and foreign training for 13 EEP personnel, conducted in two rounds of two weeks each, covering all associated costs (visa, airfare, per diem, etc.).

Training sessions will be distributed evenly over the contract period, allowing content to be tailored to evolving needs identified through inspections, audits, and ongoing field activities. In addition, the Consultant shall assess EEP’s broader capacity-building needs and implement a targeted institutional strengthening plan. This will include practical training, hands-on support, and knowledge transfer, with the ultimate goal of fostering a self-sustaining dam safety culture within the organization

The specific tasks under this assignment shall include, but are not limited to, the following:

- Assess capacity gaps in dam safety management and emergency preparedness within EEP.

- Integrate and build capacity of EEP staff by involving them in project implementation to promote knowledge transfer and sustainability.

- Design and deliver a structured capacity-building program including local training, international study tours, and technical workshops for dam safety personnel, plant managers, engineers, and emergency response teams.

- Provide hands-on support and mentoring during field activities, audits, and the rollout of the Dam Safety Management System (DSMS) to reinforce skills and embed best practices.

Deliverables of Task 7:

Training and Capacity Building Materials

Training presentations, manuals, case studies, evaluation tools, and workshop summaries.

### Overall Deliverables

Indicative deliverables for respective Tasks are listed in the sections above. The Consultant’s proposal shall include a list of deliverables commensurate with the proposed Tasks described under the Scope of Work.

### Timeline/ Schedule

Consultant shall develop a schedule to execute the individual tasks described under the Scope of Work in an expedited manner. For the purposes of expediting the site visits and condition assessments, Table 2 prioritizes the projects which is done based on our previous dam monitoring work s. The Engineering Consultant shall develop a schedule based on the priority groupings and Scope of Work.

| No, | Project Name | Priority Group | Dam Type | Capacity | Remark |
| --- | --- | --- | --- | --- | --- |
| 1 | Gibe III HEPP | 1 | Gravity Roller Compacted Concrete (RCC) | 1870MW |  |
| 2 | Koka | 2 | Concrete Gravity Dam | 43.2 MW | both are found in the same geographic location/the same direction |
| 3 | Awash II/III | 3 | Syphon Weir | 32 MW/32 MW |  |
| 4 | Tekeze | 4 | Double Curvature Arch Dam | 300 MW |  |
| 5 | Melka Wakena | 5 | Earth & Rock-fill Dam | 153 MW | both are found in the same geographic location/the same direction |
| 6 | Genale Dawa III | 6 | Concrete Faced Rock fill Dam | 254 MW |  |
| 7 | Gibe I | 7 | Rock fill asphalt faced | 184 MW | >> |
|  | Gibe II |  | Mass Concrete Weir | 420 MW |  |
| 8 | Tana Beles (Lake) | 8 | Lake Tana | 460 MW254 MW | >> |
| 9 | Tis Abay I/II | 9 | concrete weir | 12 MW/72 MW |  |
| 10 | Fincha main dam plus Amerti reservoir | 10 | Earth & Rock-fill | 134 MW | >> |
| 11 | Fincha Amerti Neshe | 11 | Homogeneous Earth fill (Embankment) | 97 MW |  |
| 12 | Grand Ethiopian Renaissance Dam (GERD) | 12 | Roller-compacted concrete gravity | 5,150 MW |  |

Table 2: Project Priority

### Reporting

The consultant will provide regular progress reports to the EEP management team and will work closely with the EEP staff to ensure that all aspects of the project are conducted in accordance with the EEP policies and procedures.

### Consultant’s team and Qualifications

| Taks |  | Key Staff |
| --- | --- | --- |
| Task 1 | Documentation Review | Team Leader |
|  |  | Dam Safety specialist / Risk Assessment Expert |
|  |  | Geotechnical Engineer |
|  |  | Dam Safety Institutional Expert |
|  |  | others |
| Task 2 | Comprehensive Project Current Condition Assessment | Team Leader |
|  |  | Dam Safety specialist / Risk Assessment Expert |
|  |  | Instrumentation and Monitoring Specialist |
|  |  | Geotechnical Engineer |
|  |  | Structural Engineer |
|  |  | Hydromechanical/electro-mechanic engineer |
| Task3 | Detail Safety Assessment (PFMA) and Investigations | Team Leader |
|  |  | Dam Safety specialist / Risk Assessment Expert |
|  |  | Instrumentation and Monitoring Specialist |
|  |  | Geotechnical Engineer |
|  |  | Structural Engineer |
|  |  | others |
| Task 4 | Employer Representative for Maintenance | Team Leader |
|  |  | Dam Safety Management Specialist/ |
|  |  | Dam Safety specialist / Risk Assessment Expert |
|  |  | Instrumentation and Monitoring Specialist |
|  |  | EPP Expert |
| Task 5 | Inspection and audit | Dam Safety specialist / Risk Assessment Expert |
|  |  | Instrumentation and Monitoring Specialist |
|  |  | Geotechnical Engineer |
|  |  | Structural Engineer |
| Task6 | Development of Dam Safety Management Program | Team Leader |
|  |  | Geotechnical Engineer |
|  |  | Dam Safety Institutional Expert |
|  |  | Hydromechanical/electro-mechanic engineer |
| Task7 | Capacity Building | Team Leader |
|  |  | Training specialist |
|  |  | Instrumentation and Monitoring Specialist |
|  |  | Dam Safety specialist / Risk Assessment Expert |
|  |  | Others as necessary |

The Consultant shall deploy a qualified multidisciplinary team to perform the scope of services. The assignment will require specialized expertise across dam safety, engineering, instrumentation, institutional, and training domains.

| Position | Minimum Education | Professional Experience | Relevant Specialization/ Tasks |  | Additional Requirements |
| --- | --- | --- | --- | --- | --- |
| Team Leader | Master’s or higher in Civil/Hydraulic/Geotechnical Engineering (or related) | ≥ 13 years | Overall project leadership, coordination of multidisciplinary teams, quality assurance, stakeholder engagement |  | Prior experience as Team Leader/Project Manager on ≥ 3 similar assignments |
| Dam Safety Specialist / Risk Assessment Expert | M.Sc. in Civil/Hydraulic Engineering or related | ≥ 11 years | Dam safety reviews, risk assessment, PFMA, RIDM |  | Participation in ≥ 6 dam safety projects |
| Dam Safety Management Specialist | M.Sc. in Water Resources / Civil Engineering or equivalent | ≥ 11 years |  | Development of dam safety management frameworks, institutional strengthening | Experience with policy, governance, or regulatory frameworks |
| Instrumentation & Monitoring Specialist | B.Sc. in Civil/Geotechnical/Electrical Engineering | ≥ 10 years |  | Installation, operation, and data interpretation of dam monitoring instruments | Strong field experience in instrumentation troubleshooting |
| Geotechnical Engineer | B.Sc./M.Sc. in Geotechnical/Geological Engineering | ≥ 10 years |  | Foundation assessment, slope stability, seepage analysis, rim stability | Experience with ≥ 5 hydropower/dam projects |
| Structural Engineer | B.Sc./M.Sc. in Structural/Civil Engineering | ≥ 9 years |  | Stability of dam structures, powerhouse, spillways, appurtenant works | Experience in RCC/concrete dams preferred |
| Hydro mechanical / Electromechanical Engineer | B.Sc. in Mechanical/Electrical Engineering | ≥ 9 years |  | Inspection and assessment of gates, valves, turbines, hoists, cranes, and auxiliary systems | Field-based hydro mechanical equipment expertise required |
| EPP Expert (Emergency Preparedness Planning) | B.Sc./M.Sc. in Civil Engineering, Water Resources, or related | ≥ 8 years |  | Preparation of dam emergency preparedness and response plans | Experience with hazard mapping and dam break studies |
| Training Specialist | B.A./B.Sc. in Education, Engineering, or related field | ≥ 10 years |  | Design and delivery of technical training and capacity-building programs | Demonstrated experience in hydropower/dam safety training |

| S No | Key Staff | Qty | Mam Month |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- |
|  |  |  | Task 1 | Task 2 | Task 3 | Task 4 | Task 5 | Total |
| 1 | Team Leader |  |  |  |  |  |  |  |
| 2 | Dam Safety specialist / Risk Assessment Expert |  |  |  |  |  |  |  |
| 3 | Dam Safety Management Specialist/ |  |  |  |  |  |  |  |
| 4 | Instrumentation and Monitoring Specialist |  |  |  |  |  |  |  |
| 5 | Geotechnical Engineer |  |  |  |  |  |  |  |
| 6 | Structural Engineer |  |  |  |  |  |  |  |
| 7 | Hydromechanical/electro-mechanic engineer |  |  |  |  |  |  |  |
| 8 | EPP Expert |  |  |  |  |  |  |  |
| 9 | Training specialist |  |  |  |  |  |  |  |
|  | Others |  |  |  |  |  |  |  |

### Consultant’s proposal

The Consultants’ proposals for Dam Monitoring and Development of a Dam Safety Management System (DSMS) of EEP shall contain the sections (information) listed below.

- Work Approach/Methodology - The scope of work shall include a description of the specific activities that will be performed to accomplish the required tasks identified in this Terms of Reference. This should include any proposed documents to be reviewed and meetings to conduct, field surveys, etc.  If the Consultant feels that additional tasks or activities within the scope of work are required or warranted, these shall be stated and delineated as “Optional Tasks”.

- Project Team and Qualifications - This shall include the name of the principal staff members (indicated above). Qualifications of staff should include relevant technical capabilities, previous relevant project experience, specific experience and knowledge on institutional environmental and social capacity assessment, and specific language skills.

- Schedule - A proposed schedule for performance of the consultancy service must be presented with breakdown of specific tasks and activities. The schedule must indicate the proposed start and completion dates for each activity listed in the “Scope of Work” section of this Terms of Reference and any important or specific Project milestones (e.g., report submission).

- Estimated Costs - A total cost of the consultancy service must be provided. Breakdown of the estimated costs by tasks/activities must also be presented (e.g., tabular format) and should include Direct Labor Costs (number of days per staff and their associated unit costs) and reimbursable expenses (e.g., travel, per diem, etc.). Any assumptions related to the estimated costs must be clearly stated.  If any additional Optional Tasks are recommended, then a separate cost estimate must be provided.

### Client’s support

The Client will support the Consultants in the following matters:

- Access to relevant documents of EEP including policies, procedures, manuals, and guidelines relevant to Dam Monitoring and Safety Management System.

- Support (whenever possible) the Consultant’s meetings and field surveys and liaison with the concerned officials and personnel.

The Consultant will work with counterpart staff from EEP's Generation Operation Dam management and experts assigned by the client to build capacity.

### List of enclosure

Annex-1 Basic Features of all the hydropower dams attached.

1. GILGEL GIBE-I HYDRO ELECTRIC POWER STATION

| Plant Installed Capacity | 184 MW |
| --- | --- |
| No. and size of Units | 3 units of 70 MW each |
| Location | 263 KM south west of Addis Ababa |
| Annual Generation Capacity | 722 MU |
| Reservoir: |  |
| Reservoir Area at FRL | 51 sq. km |
| Maximum Level | 1671 m |
| Minimum Level | 1653 m |
| Total Storage Capacity at FRL | 839 Mn. M3 |
| Power Storage Capacity (Live Storage) | 668 Mn. M3 |
| Dead Storage | 171 Mn. M3 |
| Dam: |  |
| Type | Rockfill asphalt faced |
| Crest Elevation | 1675 m |
| Crest Length | 1700 m |
| Max. height | 41 m |
| Spillway: |  |
| Type of gate | Flap gate |
| No. of Gates | 4 |
| Height | 5.8 m |
| Max. Discharge | 2253 m3/sec. |
| Intake: |  |
| Type of gate | Cylindrical Gate |
| No. of Gates | 1 |
| Diameter * Height | 6.5 m * 4 m |
| Rated Design Flow | 100 m3/sec. |
| Powerhouse: |  |
| Type | Underground |
| Dimension | 83 x 40 x 22.5 (L*W*H) |
| Installed Capacity | 184 MW |
| Water Conductor System: |  |
| Power Tunnel Length | 9205 m |
| Diameter | 5.5m |
| Surge Shaft: |  |
| Diameter | 14m |
| Height | 110m |
| Penstock: |  |
| Type | Underground, Steel lined |
| Diameter | 5m |
| Length | 711 m |
| Vertical Shaft Depth | 166 m |
| Manifold Dia. | 5/4.1/2.9 m |
| Max. Design Pressure | 3.5 MPa |
| Turbine: |  |
| Make: | Voith Siemens |
| Type: | Francis, Vertical |
| Rated Head: | 223.37 Mtr. |
| Rated Output: | 3 x 70.04 MW |
| Rated Discharge: | 33.908 Cu.Mtr/Sec |
| Rated Speed: | 428.6 RPM |
| Governor(New): | Electronic Digital Governor |
| Type of MIV | Spherical |
| Generator: |  |
| Make | VA Tech |
| Type | 3-Phase Synchronous Generator |
| Rated continuous power, (MVA) | 73 MVA |
| Power Factor | 0.9 |
| Generator voltage, (kV) | 13.8 ± 5 % |
| Rated Stator Current | 3054.1 A |
| Type of Excitation | Static |
| Rated Excitation Current | 1030 A |
| Rated Excitation Voltage | 144 V |
| GSU Transformer: |  |
| No. of phases | Three |
| Installation | Outdoor |
| Rated MVA | 3 X 73 MVA |
| Type of cooling | OFWF |
| Rated Voltage | 13.8 / 230 kV |
| Power Transformer: |  |
| No. of phases | Three |
| Installation | Outdoor |
| Rated MVA | 1 X 40 MVA |
| Type of cooling | OFWF |
| Rated Voltage | 230 / 132 kV |
| Switchyard: |  |
| No. of Outgoing Feeders | 3 (one no. 132 kV & two 230kV) |
| Rated Voltage | 230 / 132 kV |

2. GILGEL GIBE-II HYDRO ELECTRIC POWER STATION

| General: |  |
| --- | --- |
| Plant Installed Capacity | 420 MW |
| No. and size of Units | 4 units of 105 MW each |
| Annual Generation Capacity | 1244 MU |
| Reservoir: |  |
| Normal Operating Level | 1431.5 m.a.s.l |
| Minimum Operating Level | 1424.0 m.a.s.l |
| Dead Storage | 0.96 Mn. m3 |
| Live Storage | 1.3 Mn. m3 |
| Storage Weir: |  |
| Type | Mass Concrete Weir |
| Height | 56 m. |
| Powerhouse: |  |
| Type | Surface |
| Installed Capacity | 420 MW |
| Water Conductor System: |  |
| HRT Length | 25860 m |
| Internal Diameter | 6.3 m |
| No. of Penstock | 2 |
| Internal Dia. Of Penstock | 3.6m down to 2.8m |
| Nominal Flow each | 51 m3/s |
| Length | 1.2 km each |
| SURGE SHAFT: |  |
| Height | 95m |
| Diameter | 18m |
| TURBINE: |  |
| Type: | Pelton, Vertical |
| Rated Head: | 485 Mtr. |
| Rated Output: | 4 x 107 MW |
| Rated Discharge: | 24.531 Cu.Mtr/Sec |
| Rated Speed: | 333.33 RPM |
| MIV: |  |
| Type of MIV | Spherical |
| Diameter | 1.9 m |
| Generator: |  |
| Type | 3-Phase Synchronous Generator |
| Rated continuous power, (MVA) | 125 MVA |
| Power Factor | 0.85 |
| Generator voltage, (kV) | 15 |
| Rated Stator Current | 4811 A |
| Insulation Class | F |
| Type of Excitation System | Static |
| GSU Transformer: |  |
| Type | 3-Phase OFW |
| No. of phases | Three |
| Installation | Outdoor |
| Rated MVA | 125 MVA |
| Type of cooling | OFWF |
| Rated Voltage | 15 / 400 kV |
| Switchyard: |  |
| No. of Outgoing Feeders | 2 |
| Type of Bus bar | Double Bus |
| Rated Voltage | 400 kV |

3. GIBE-III HYDRO ELECTRIC POWER STATION

4.KOKA HYDRO ELECTRIC POWER STATION

| General: |  |
| --- | --- |
| Plant Installed Capacity | 43.2 MW |
| No. and size of Units | 3 units of 14.4 MW each |
| Location | 81 KM south east of Addis Ababa |
| Annual Generation Capacity | 110 MU |
| Reservoir: |  |
| Reservoir Area at FRL | 23.6 sq. km |
| Minimum Level | 1580.7m |
| Total Storage Capacity at FRL | 1850 x 100,00,000 m3 |
| Power Storage Capacity (Live Storage) | 1680 x 100,00,000 m3 |
| Regulating Flow | 42.3 m3/s |
| Dam: |  |
| Type | Concrete Gravity Dam |
| Crest Elevation | 1593.2m |
| Crest Length | 458m |
| Discharge | 1000 m3/s |
| Powerhouse: |  |
| Type | Surface |
| Installed Capacity | 43.2 MW |
| Water Conductor System: |  |
| Pressure Tunnel Length | 71.5m |
| Diameter | 5.5m |
| Concrete Pipe Length | 145.37m |
| Diameter | 5.5m |
| Surge Tank: |  |
| Diameter | 18m |
| Height | 20m |
| Penstock: |  |
| Number | 3 |
| Diameter | 3.5m |
| Length | 50.7 / 55.4 / 61.1 m |
| TURBINE: |  |
| Make: | C.M Riva |
| Type: | Francis, Vertical |
| Rated Head: | 42 Mtr. |
| Rated Output: | 3 x 15.2 MW |
| Rated Discharge: | 41.5 Cu.Mtr/Sec |
| Rated Speed: | 214.3 RPM |
| Governor (New): | Electronic Digital Governor: Type-T2000S |
| Type of MIV | Butterfly |
| Generator: |  |
| Make | Ercole Marelli |
| Type | 3-Phase Synchronous Generator |
| Construction type | Umbrella |
| Rated continuous power, (MVA) | 18 MVA |
| Power Factor | 0.8 |
| Generator voltage, (kV) | 10.5 ± 10 % |
| Rated Stator Current | 990 ± 10% |
| Short circuit ratio | 1.7 |
| Excitation System: |  |
| Make | ABB Industrial S.P.A |
| Type | Static |
| Nominal Voltage | 193 V |
| Nominal Current | 740 A |
| GSU Transformer: |  |
| Type | 3 Winding- 3-Phase OFW |
| No. of phases | Three |
| Installation | Outdoor |
| Rated MVA | 3 X 18/18/6 MVA |
| Type of cooling | OFWF |
| Vector group | Delta/star/star; |
| Rated Voltage | 10.5/135/15KV |
| Impedance Voltage | 10/8.5/4 % on 18/6/6 base |
| Switchyard: |  |
| No. of Outgoing Feeders | 5 |
| Type of Bus bar | Double Bus |
| Rated Voltage | 132 kV |
| Maximum Service Voltage | 156 kV |

5.TEKEZE HYDRO POWER STATION

| General: |  |
| --- | --- |
| Plant Installed Capacity | 300 MW |
| No. and size of Units | 4 units of 75 MW each |
| Type of Powerhouse | Underground |
| Annual Generation Capacity | 981 MU |
| Reservoir: |  |
| Reservoir Area | 156.88 km2 |
| Dead Storage Capacity | 4,000,000,000 m3 |
| Operational Storage capacity | 5,300,000,000 m3 |
| Catchment Area | 45,694 km2 |
| Dam: |  |
| Type | Double Curvature Arch Dam |
| Crest Elevation | 1145 m |
| Height | 188 m |
| Crest Length | 420 m |
| Water Conductor System: |  |
| Head race Tunnel: |  |
| Length | 320 m |
| Diameter | 7.25 m |
| Low Pressure Tunnel: |  |
| Diameter | 6.75 m |
| Length | 24 m |
| Tail Race Tunnel: |  |
| Diameter | 5 m |
| Length | 73 m |
| Penstock: |  |
| Diameter | 6.75 m |
| Length | 120 m |
| TURBINE: |  |
| Type: | Francis, Vertical |
| Rated Head: | 156 M |
| Rated Discharge: | 52.04 m3/s |
| Rated Speed: | 300 RPM |
| Type of MIV | Butterfly |
| Generator: |  |
| Type | 3-Phase Synchronous Generator |
| Rated continuous power | 86.7 MVA |
| Power Factor | 0.9 |
| Generator voltage, (kV) | 13.8 kV |
| Rated Stator Current | 3627.3 A |
| Excitation System: |  |
| Type | Static |
| Nominal Voltage | 240 V |
| Nominal Current | 1250 A |
| GSU Transformer: |  |
| Type | 3-Phase |
| Installation | Outdoor |
| Rated MVA | 90 MVA |
| Type of cooling | ODAF |
| Vector group | YNd11 |
| Rated Voltage | 13.8 / 230 kV |
| Switchyard: |  |
| No. of Outgoing Feeders | 2 |
| Type of Bus Bar | Double Bus bar |
| Rated Voltage | 230 kV |
| Type of Circuit Breakers | SF6 |

6.TIS ABAY-I & II HYDRO POWER STATIONS

| Common Features |  |  |
| --- | --- | --- |
| Lake Tana: |  |  |
| Surface Area | 3000 km2 |  |
| Total Volume (below El. 1787) | More than 20,000 Mm3 |  |
| Catchment Area | 15,300 km2 |  |
| Spill Level (Still of Chara Chara Weir) | 1787.00 m |  |
| Minimum Operation Level | 1784.00 m |  |
| Storage between 1787.0 & 1784.0 | 9100 Mm3 |  |
| No. of Radial Gates at Chara Chara | 7 |  |
|  | TIS ABAY-I | TIS ABAY-II |
| General: |  |  |
| Plant Installed Capacity | 12 MW | 72 MW |
| No. and size of Units | 3 units of 4 MW each | 2 units of 36 MW each |
| Type of Powerhouse | Surface | Surface |
| Annual Generation Capacity | 50 MU | 359 MU |
| Turbine: |  |  |
| Type: | Francis, Vertical | Francis, Vertical |
| Rated Head: | 46 m | 53.2 m |
| Rated Output: | 4.18 MW | 36.83 MW |
| Rated Discharge: | 10m3/s | 75 m3/s |
| Rated Speed: | 375 RPM | 214.3 RPM |
| Generator: |  |  |
| Type | 3-Phase Synchronous Generator | 3-Phase Synchronous Generator |
| Rated continuous power, (MVA) | 4.8 MVA | 48 MVA |
| Power Factor | 0.8 | 0.9 |
| Generator voltage, (kV) | 6 kV | 10.5 Kv |
| Rated Stator Current | 562 A | 2199.4 A |
| Rated Excitation Voltage | 112 V | 145 V |
| Rated Excitation Current | 263 A | 1085 A |
| GSU Transformer: |  |  |
| Type | 3-Phase | 3-Phase OFW |
| Rated MVA | 4.8 MVA | 40 MVA |
| Installation | Outdoor | Outdoor |
| Rated Voltage | 6 / 45 kV | 10.5 / 132 kV |
| Type of Cooing | ONAN | ONAF |

7. AWASH-II & III HYDRO ELECTRIC POWER STATIONS

|  | Awash – II | Awash - III |
| --- | --- | --- |
| General: |  |  |
| Plant Installed Capacity | 32 MW | 32 MW |
| No. and size of Units | 2 units of 16 MW each | 2 units of 16 MW each |
| Location | 121 KM south east of Addis Ababa | 124 KM south east of Addis Ababa |
| Annual Generation Capacity | 182 MU | 182 MU |
| Reservoir: |  |  |
| Reservoir Area at FRL | 2.731 sq. km | 0.063 sq. km |
| Maximum Reservoir Level | 1535.50 m | 1471.80 m |
| Normal Reservoir Level | 1535.50 m | 1471.80 m |
| Minimum Reservoir Level | 1534.50 m |  |
| Total Storage Capacity at Max L | 2.6 x 100,00,000 m3 | 0.07 x 100,00,000 m3 |
| Power Storage Capacity (Live Storage) | 2.24 x 100,00,000 m3 |  |
| Regulating Flow | 39.9 m3/s | 39.9 m3/s |
| Dam: |  |  |
| Type | Syphon Weir | Syphon Weir |
| Crest Elevation | 1539.04 m | 1475.30 m |
| Crest Length | 88 m | 125 m |
| Max. Height | 10 m | 20 m |
| Max. Spillway Discharge | 937 m3/s | 1220 m3/s |
| Discharge | 1000 m3/s |  |
| Powerhouse: |  |  |
| Type | Surface | Surface |
| Installed Capacity | 32 MW | 32 MW |
| Surge Tank: |  |  |
| Diameter | 2 X 19.5 m | 2 X 19.5 m |
| Height | 2 X 22 m | 27.80 m |
| Penstock: |  |  |
| Number | 2 | 2 |
| Diameter | 7 m | 7 m |
| Length | 2 X 300 m | 2 X 260 m |
| Turbine: |  |  |
| Type: | Francis, Vertical | Francis, Vertical |
| Rated Head: | 58.92 m | 59.94 m |
| Rated Output: | 2 x 16 MW | 2 x 16 MW |
| Rated Discharge: | 2 X 32.8 m3/s | 2 X 33.1 m3/s |
| Rated Speed: | 300 RPM | 300 RPM |
| Type of MIV | Butterfly | Butterfly |
| Generator: |  |  |
| Type | 3-Phase Synchronous Generator | 3-Phase Synchronous Generator |
| Rated continuous power, (MVA) | 2 X 20 MVA | 2 X 20 MVA |
| Power Factor | 0.8 | 0.8 |
| Generator voltage, (kV) | 10.5 ± 10 % | 10.5 ± 10 % |
| Rated Stator Current |  |  |
| Type of Excitation System | Static | Static |
| GSU Transformer: |  |  |
| Type | 3 Winding- 3-Phase OFW | 3 Winding- 3-Phase OFW |
| No. of phases | Three | Three |
| Installation | Outdoor | Outdoor |
| Vector group | Delta/star/star; | Delta/star/star; |
| Rated Voltage | 141.75 + 2 X 2.5%/15/10.5 KV | 141.75 + 2 X 2.5%/15/10.5 KV |

- FINCHA’A- AMERTI- NESHE HYDRO POWER STATION

| General: |  |
| --- | --- |
| Plant Installed Capacity | 97 MW |
| No. and size of Units | 2 units of 48.5 MW each |
| Location | 300km North-West of Addis Ababa |
| Annual Generation Capacity | 230 MU |
| Reservoir: |  |
| Normal Water level | 2230 m |
| Dead Water Level | 2214 m |
| Total Reservoir Capacity | 448,000,000 m3 |
| Active Storage | 363,000,000 m3 |
| Dead Storage | 85,000,000 m3 |
| Dam: |  |
| Type | Homogeneous Earthfill (Embankment) Dam with horizontal & central inclined filter blanket. |
| Crest Elevation | 2235 m |
| Height | 35 m |
| Crest Length | 1000 m |
| Powerhouse: |  |
| Type | Surface |
| Installed Capacity | 97 MW |
| Water Conductor System: |  |
| Low Pressure Pipe Line: |  |
| Length | 933.6 m |
| Diameter | 2.7 m |
| Low Pressure Tunnel: |  |
| Diameter | 2.5 m / 2.7 m |
| Length | 828 m |
| Surge Tank: |  |
| Diameter | 3 m |
| Height | 85 m |
| Pressure Shaft: |  |
| Length | 218 m (198.5 m steel lined & 19.5 m reinforced concrete) |
| High Pressure Tunnel: |  |
| Diameter | 2.1 m |
| Length | 532.5 m |
| Maximum Flow velocity | 5.6 m/s |
| Penstock: |  |
| Diameter | 2.1 m |
| Length | 1.5 km |
| Turbine: |  |
| Type: | Pelton, Vertical |
| Rated Head: | 587.5 M |
| Rated Output: | 48.82 MW |
| Rated Discharge: | 9.35 m3/s |
| No. of Nozzles | 5 |
| Rated Speed: | 500 RPM |
| Type of MIV | Spherical |
| Generator: |  |
| Make | Harbin Electric Machinery Co., China |
| Type | 3-Phase Synchronous Generator |
| Construction type | Suspended |
| Rated continuous power | 53 MVA |
| Power Factor | 0.9 |
| Generator voltage, (kV) | 13.8 kV |
| Rated Stator Current | 2217.7 A |
| Excitation System: |  |
| Type | Static |
| Nominal Voltage | 153.9 V |
| Nominal Current | 976.7 A |
| GSU Transformer: |  |
| Type | 3-Phase |
| No. of phases | Three |
| Installation | Outdoor |
| Rated MVA | 53 MVA |
| Type of cooling | OFAF |
| Vector group | YNd1 |
| Rated Voltage | 13.8 / 230 kV |
| Switchyard: |  |
| No. of Outgoing Feeders | 1 |
| Type of Bus bar | Single Bus |
| Rated Voltage | 230 kV |
| Type of Circuit Breakers | SF6 |

9.FINCHA HYDRO ELECTRIC POWER STATION

| General: |  |
| --- | --- |
| Plant Installed Capacity | 134 MW |
| No. and size of Units | 3 units of 33.25 MW each & 1 unit of 38 MW |
| Location | 300km north-west of Addis Ababa |
| Annual Generation Capacity | 760 MU |
| Reservoir: |  |
| Reservoir Area at El. 2221.7 | 170 sq. km |
| Maximum Level | 2221m |
| Minimum Level | 2212 m |
| Spillway Crest Level | 2219m |
| Total Storage Capacity at Spillway Crest Level | 625 km3 |
| Regulating Flow | 12.7 m3/s |
| Dam: |  |
| Type | Earth & Rock-fill |
| Crest Elevation | 2225m |
| Crest Length | 340m |
| Height | 22.2m |
| Powerhouse: |  |
| Type | Surface |
| Installed Capacity | 134 MW |
| Water Conductor System: |  |
| Tunnel: |  |
| Length | 3523m |
| Diameter | 3m |
| Surge Shaft: |  |
| Diameter | 7m |
| Height | 50m |
| Penstock: |  |
| Number | 1 |
| Diameter | 2.1m |
| Length | 1917m (558m underground & 1359m exposed) |
| Turbine: |  |
| Type: | Pelton, Vertical |
| Rated Head: | 517 M |
| Maximum Output: | 34.1 MW |
| Maximum Discharge: | 7.42 m3/s |
| Rated Speed: | 500 RPM |
| No. of jets / unit | 4 |
| Type of MIV | Spherical |
| Generator: |  |
| Type | 3-Phase Synchronous Generator |
| Construction type | Vertical Suspended |
| Rated continuous power, (MVA) | 35 MVA |
| Maximum output | 40 MVA |
| Power Factor | 0.95 |
| Generator voltage, (kV) | 13.8kV |
| Excitation System: |  |
| Type | Static |
| Nominal Voltage | 165 V (old units) |
| Nominal Current | 670 A (old units) |
| GSU Transformer: |  |
| Type | 2 Winding- 3-Phase OFAF |
| Installation | Outdoor |
| Rated MVA | 40 MVA |
| Vector group | YNd1 |
| Rated Voltage | 13.8 / 230 kV |
| Switchyard: |  |
| No. of Outgoing Feeders | 3 |
| Type of Bus bar | Single / Double Bus |
| Rated Voltage | 230 kV |
| Type of Circuit Breakers | SF6 |

10.MELKA WAKENA HYDRO ELECTRIC POWER STATION

| General: |  |
| --- | --- |
| Plant Installed Capacity | 153 MW |
| No. and size of Units | 4 units of 38.25 MW each |
| Location | 280 KM south east of Addis Ababa |
| Annual Generation Capacity | 543 MU |
| Reservoir: |  |
| Storage Capacity | 763 x 106 m3 |
| Usable Storage Capacity | 606 x 106 m3 |
| Dead Storage capacity | 157 x 106 m3 |
| Maximum Level | 2522.9 m |
| Normal Level | 2520.7 m |
| Minimum Level | 2508 m |
| Dam: |  |
| Type | Earth & Rock-fill Dam |
| Crest Length | 2 km |
| Height | 42 m |
| Powerhouse: |  |
| Type | Surface |
| Installed Capacity | 153 MW |
| Water Conductor System: |  |
| Head Race Canal: |  |
| Length | 7.2 km |
| Discharge | 60 cumecs |
| Vertical Shaft: |  |
| Diameter | 4.2 m |
| Height | 300 m |
| Penstock: |  |
| Diameter | 4.2 m |
| Length | 535 m |
| Turbine: |  |
| Type: | Francis, Vertical |
| Rated Head: | 297 M. |
| Rated Output: | 4 x 39.2 MW |
| Rated Discharge: | 14.73 m3/s |
| Rated Speed: | 600 RPM |
| Generator: |  |
| Type | 3-Phase Synchronous Generator |
| Rated continuous power, (MVA) | 45 MVA |
| Power Factor | 0.85 |
| Generator voltage, (kV) | 13.8 kV |
| GSU Transformer: |  |
| Type | 3-Phase |
| No. of phases | Three |
| Installation | Outdoor |
| Rated MVA | 45 MVA |
| Rated Voltage | 13.8 / 230 KV |
| Switchyard: |  |
| No. of Bays | One no. DC 230kV & One no. SC 132kV |
| Type of Bus bar | One main & one transfer |
| Rated Voltage | 230 kV / 132 kV |
| Type of Circuit Breakers | Air Blast CB |

11.TANA BELES HYDRO ELECTRIC POWER STATION

| General: |  |
| --- | --- |
| Plant Installed Capacity | 460 MW |
| No. and size of Units | 4 units of 115 MW each |
| Annual Generation Capacity | 2051 MU |
| Reservoir: |  |
| Full Storage Level | 1787 m |
| Minimum Operating Level | 1784 m |
| Total Storage at FSL | 32273 Mm3 |
| Live Storage | 9126 Mm3 |
| Dead Storage | 23147 Mm3 |
| Catchment Area | 15320 km2 |
| Powerhouse: |  |
| Type | Underground |
| Installed Capacity | 460 MW |
| Water Conductor System: |  |
| Diameter of Low Pressure Head Race Tunnel | 7.2 m |
| Diameter of Penstock vertical shaft | 6.0 m |
| Diameter of High Pressure Head race Tunnel | 5.6 m |
| Manifold Dia. | 5.6 / 4.0/ 2.8 m |
| Surge Shaft: |  |
| Diameter | 18m |
| Height | 91.2m |
| TURBINE & MIV: |  |
| Type: | Francis, Vertical |
| Rated Head: | 315 m |
| Rated Output: | 1154 MW |
| Rated Discharge: | 40 cumecs |
| Rated Speed: | 375 RPM |
| Type of MIV | Spherical |
| Diameter of MIV | 2.2 m |
| Generator: |  |
| Type | 3-Phase Synchronous Generator |
| Rated continuous power, (MVA) | 133 MVA |
| Power Factor | 0.9 |
| Generator voltage, (kV) | 15 kV |
| GSU Transformer: |  |
| Type | 3-Phase, Oil Immersed |
| No. of phases | Three |
| Installation | Indoor |
| Rated MVA | 133 MVA |
| Type of cooling | OFWF |
| Vector group | YNd11 |
| Rated Voltage | 15 / 400 KV |
| Switchyard: |  |
| No. of Outgoing Feeders | 2 |
| Type of Bus bar | Double Bus |
| Rated Voltage | 400 kV |
| Type of Circuit Breakers | SF6 |
| Type of Circuit Breakers | SF6 |

- GENALE DAWA-3 HYDRO ELECTRIC POWER STATION